## Shift_Data
Mixing Operation — 8 Hour Shift: Actual vs Target Output
Example dataset. Target = owner-stated ideal output per hour. Hours 1-3 met target; hours 4-8 did not, each with a supervisor-logged reason categorized under the 4M framework (Manpower, Process, Material, Machine).
Hour | Time window | Target output (batches) | Actual output (batches) | Variance (batches) | Variance % | Target met? | Supervisor reason | Category (4M)
1 | 06:00 - 07:00 | 5 | 5 | 0 | 0% | Yes | Manpower fully staffed, no issues | -
2 | 07:00 - 08:00 | 5 | 5 | 0 | 0% | Yes | Line running to standard | -
3 | 08:00 - 09:00 | 5 | 5 | 0 | 0% | Yes | Line running to standard | -
4 | 09:00 - 10:00 | 5 | 3 | -2 | -40% | No | One operator pulled for break coverage on adjacent line, mixer ran short-handed | Manpower
5 | 10:00 - 11:00 | 5 | 3 | -2 | -40% | No | Incoming flour batch tested high moisture; extra dry-mix time added before wet mix | Material
6 | 11:00 - 12:00 | 5 | 2 | -3 | -60% | No | Mixer motor overheated mid-shift; RPM reduced to prevent trip, cycle time increased | Machine
7 | 12:00 - 13:00 | 5 | 3 | -2 | -40% | No | Operator followed outdated mixing sequence (SOP not updated at station); one batch reworked | Process
8 | 13:00 - 14:00 | 5 | 3 | -2 | -40% | No | Two operators on lunch rotation overlap left mixer under-staffed for 20 minutes | Manpower
| Shift totals | 40 | 29 | -11 | -27.5%
Mismatch reasons by category (4M)
| Category | Hours affected | Batches short
| Manpower | 2 | 4
| Process | 1 | 2
| Material | 1 | 2
| Machine | 1 | 3
Legend
Green row = target met ¦ Red row = target not met
Category colors: Manpower = blue, Process = purple, Material = amber, Machine = coral
Target of 5 batches/hour is an example owner-stated ideal; replace with real plant standard.